## Plan
Work list
1 | Admin Panel to improve
2 | New Platform on Wordpress
3 | SEO of jansatyagrah.in
1 | To find out the bugs area, Will fix those
No considerable timing will be taken
2 | To do more homework for possible options;
Consult in circle: Ashish
| Finalise the platform | 2017-06-20
| Architecture design & Technology selection | 2017-06-23
| Segregation of work | 2017-06-28

## Nw Site
To do more homework for possible options;
Consult in circle: Ashish
| Finalise the platform | 2017-06-20
| Architecture design & Technology selection | 2017-06-23
| Segregation of work | 2017-06-28
Project timeline
1 | Beta Version of Website | 20th July
2 | Testing, Fixes, Feedback, Improvements | 5th August
3 | Training | 11th August
4 | Project live | 15th August
Development steps
1 | Market study, mainly competitors | 2017-06-20
2 | Technologies selection | 2017-06-22
3 | Architecture & DB structure to design | 2017-06-29
4 | Theme selection, Sitemap | 2017-06-30
5 | Coding | 2017-07-09
6 | Plugins | 2017-07-16
7 | Deploy | 2017-07-20

## Technology
Required Tech. | Type | Name
| SSL | Comodo SSL
Lets Encrypt
| Widgets | reCAPTCHA
| DocInfo | Content Security Policy
| Java Script | Facebook for Websites
| Java Script | Facebook SDK
| Advertising | Facebook Custom Audiences
| DocInfo | Twitter Cards
| DocInfo | Windows 8 Pinning
| Email Hosting Providers | ?
WordPress also features integrated link management; a search engine–friendly, clean permalink structure; the ability to assign multiple categories to posts; and support for tagging of posts.
Automatic filters are also included, providing standardized formatting and styling of text in posts (for example, converting regular quotes to smart quotes).
WordPress also supports the Trackback and Pingback standards for displaying links to other sites that have themselves linked to a post or an article.
Wordpress MU | WordPress MU makes it possible for those with websites to host their own blogging communities, as well as control and moderate all the blogs from a single dashboard.
Constantly to take the updates is necessary
Developers can also use tools to analyze potential vulnerabilities, including WPScan, WordPress Auditor and WordPress Sploit Framework developed by 0pc0deFR
WPScan is a WordPress specific security scanner.
Social Media | Sharing posts to social networks is the matter of a single click, and visitors can easily subscribe to sub feeds from a website via their most preferred feed readers including email clients.
Coding Wizard for Coding | coding wizards continue to enjoy the advantage of their skills, using which they can customize the very look and feel of their WordPress websites.
The visual editor of WordPress is as easy as using MS Word, and that’s as easy as it can get.
More & more plugins | The urge to install even rarely useful plugins can easily lead to an overdose of plugins for your WordPress website. Too many plugins slow the script and the impact is felt while you begin creating your web pages using WordPress editor.
http://www.webbuildersguide.com/website-builder-articles/pros-and-cons-of-wordpress/

## Queries
DocInfo | Twitter Cards
DocInfo | Content Security Policy
reCAPTCHA | Widgets
Content Delivery Network
SEO friendly plugins
Word Press
| Pros | Cons
| Less Dev time | Speed
SEO friendly
| Many Plugins ready | Will not difference similar apperance;
If want to create some customisation, then responsive designer be present
Unnecessary updates
Security if unverified plugins
Difficulty when complexity improve